|  |  |
| --- | --- |
| Completion/ Projected Completion | TSCA Risk Evaluation Element |
| Released on March 20, 2019 | Preliminary TSCA High Priority Designation |
| December 2019 | Final TSCA High Priority Designation   * The Official Start of the Risk Evaluation Clock |
| December 2019 | Publication of a Preliminary List that Identifies Manufacturers   * Published at the time of Final High Priority Designation * 30 Day Public Comment Period |
| April 2020 | Draft TSCA Scoping Document   * 90 Days After Final High Priority Designation * 45 Day Public Comment Period |
| August 2020 | Final TSCA Scoping Document   * 180 Days After Final High Priority Designation |
| September 2020 | Publication of a Final List of Manufacturers Responsible for Payment |
| November 2020 | Payment of TSCA Risk Evaluation Fees   * 120 Days After Final Scoping Document |
| June 2021 | Publication of a Revised Final List of Manufacturers Responsible for Payment |
| June 2021 | Publication of TSCA Health and Safety Data Reporting Rule - Addition of 20 High-Priority Substances |
| December 2021 | Submission Deadline for Unpublished Studies Pursuant to TSCA Health and Safety Data Reporting Rule |
| March 14, 2024 | Draft TSCA Risk Evaluation Released   * 60 Day Public Comment Period |
| May 7, 2024 | Virtual SACC Meeting on Charge Questions   * May 3rd comment deadline |
| May 14, 2024 | Comment Deadline for Draft TSCA Risk Evaluation |
| May 20-23, 2024 | 4-Day Virtual SACC Peer Review   * Opportunity for Public Comment |
| Estimated by December 2024 | Projected Final TSCA Risk Evaluation   * Will include risk determination of whether formaldehyde constitutes an “unreasonable risk” |
| Estimated by December 2025 | Propose risk management rule(s) for any unreasonable risk determinations found in the final risk evaluation   * Due within 1 year after publishing a final risk evaluation |
| Estimated by December 2026 | Finalize risk management rule(s) for any unreasonable risk determinations found in the final risk evaluation   * Due within 2 years after publishing the final risk evaluation * EPA may extend these deadlines for up to two years provided the aggregate length of extensions for the section 6(a) rulemaking and the risk evaluation does not exceed 2 years. |
| Estimated December 2026-2031  Within 5 Years of Risk Management Rule | Establish mandatory compliance date(s) for restrictions or the start of a ban or phase-out based on final risk management rules.   * Due within 5 years after a risk management rule is promulgated |